## Slide 1: Reviewer’s comments to Hyper-K
Can you tell us about the funding model for Hyper-K ... what requests will be made from what entities in Japan (on what time scale), what is the expected requests from foreign partners and how will foreign contributions be handled (i.e. IKC, cost book, etc.)?
What plans/thinking is in place for the project management of Hyper-K, both in terms of the construction of the detector hardware and software and in terms of building the collaboration and getting it prepared for the science?

## Slide 2
*Crude estimation to be revised by actual design and production by foreign partners
item | Japan | Oversea
J-PARC upgrade | 32 | -
Near Detector Facility | 10 | -
Near Detector | - | 30*
Total | 42 Oku-yen | 30 Oku-yen
item | Japan | Oversea
Cavern | 263 | 
Tank (liner, structure) | 127 | 
Photo-detection system | 113 | 124*
Water & management | 47 | 
Total | 549 Oku-yen | 124 Oku-yen
UTokyo
(ICRR)
KEK
Foreign partners
Period
  Construction of Hyper-K, ND, Beam upgrade: ~7 years (2020~2027)
  Operation of Hyper-K: 20 years (2027-2046)
  Operation of J-PARC: 10 years (2027-2036)
Components to be requested and institutes (Oku-yen~1MUSD, numbers for last year’s budget request)
2￼

## Slide 3: International Contributions Towards the Construction and Operation HK proto-collaboration, March 24, 2017
International proto-collaboration from non-Japanese institutions will make their best efforts, by means of in-kind and capital contributions, as well as collaboration-supplied manpower, to provide following:

## Slide 4
International sharing under discussion
•Preparing “Expression of Interests” by each countries
•To be reviewed in the HK Advisory committee on June 25-26 and HK Financial Forum on June 27-28

## Slide 5
Director
NNSO
Spokesperson, co-SP
Beam
HK proto-collaboration
→HK collaboration
KEK
Vice-director
Advisory Board
Executive Board
UTokyo
President
?
MoU
Financial committee
MoU
FA-country1
FA-country2
…
Steering Committee
Speakers Board
Publication Board
Resource Review
PM
HK-detector project office
Administration
Administration
Water
construction
Tank
construction
DAQ
construction
CM
Technical Coordinators*
International Board of Representative
→Institutional Board
ND280
INGRID
…
PM
HK-beam project office
Finance Office
Accel.
Beam
ND infra
?
HKPAC
?
?
Director General
Joint HK committee
Construction organization under discussion
Established
*To be assigned in Madrid
To be organized future
Cavern
construction
Channels for collaborator’s participation to construction
Channels for collaborator’s participation to construction
Administration
Finance Office
Physics
Software
Computing
…
Inner Det.
PD
+cover
+LC
+Elec
+sheet
IWC
Outer Det.
PD
+cover
+LC
+Elec
+sheet
+coil
Online
Trigger
GPS
Monitor
Slow
…
Water
Radon
…
We may form sub-working-groups.
PDs
Electronics
Technical Board may be additionally needed.
Working groups
Construction Teams
Example
Participation
Participation
science
construction
construction